Ironvale Digital Infrastructure: Q1 FY26 portfolio company update

Halcyon Infrastructure Partners Fund IV, L.P.  |  Quarter ended 31 March 2026  |  Investor Relations

Illustrative: Ironvale Digital Infrastructure is a fictional company (PE Bench)

Dear Limited Partners,

Ironvale, in which Fund IV holds a 62.0% fully diluted interest, had a solid first quarter. Revenue of $113.0M was 1.3% ahead of budget and 20.0% above Q1 FY25, adjusted EBITDA of $62.0M beat budget by $0.8M, and occupancy reached 91.9%. In May 2026 the company launched a sale process for 100% of its equity. On an illustrative basis of appraised campuses plus development at cost, less net debt, Fund IV's interest is worth about $1,967M, 4.6x its invested capital.

Q1 FY26 key metrics (US$ millions unless stated)

| Metric | Q1 FY26 | Budget | Q4 FY25 | Q1 FY25 | Source (document, page or cell) |
| --- | --- | --- | --- | --- | --- |
| Total revenue | 113.0 | 111.5 | 104.4 | 94.2 | Flash report (2.07) r10; mgmt accts (2.05) |
| Net operating income | 67.5 | 66.8 | 64.2 | 56.5 | Flash report (2.07) r14; mgmt accts (2.05) |
| Adjusted EBITDA | 62.0 | 61.2 | 57.7 | 50.4 | Flash report (2.07) r17; mgmt accts (2.05) |
| Adjusted EBITDA margin | 54.9% | 54.9% | 55.2% | 53.5% | Computed from the rows above |
| Leased MW (period end) | 202.2 | 201.0 | 200.7 | 188.6 | Flash (2.07) r21; KPI dashboard (3.06) r4 |
| Occupancy | 91.9% | 91.4% | 91.2% | 88.1% | Leased / commissioned MW (220; 214 Q1 FY25) |
| Net debt / LTM adj. EBITDA (mgmt definition) | 6.6x | n/a | 6.6x | n/a | Net debt at period end; Q1 statements (2.09), 2.03 p12 |

Performance ran ahead of plan on earlier colocation starts

Revenue beat budget by $1.5M on earlier-than-planned colocation commencements at PHX I and higher metered power reimbursements, which are passed through at cost. Revenue rose 8.2% on Q4 FY25 and lease and colocation revenue grew to $82.9M from $72.5M a year earlier. NOI of $67.5M was a 59.7% margin. Adjusted EBITDA excludes $1.7M of non-recurring sale-preparation costs. Net income was $0.4M, against a net loss of $2.1M for FY25 as a whole.

Operations held up. Fleet PUE was 1.29x, uptime 99.9996%, LTM retention 91.3% (MW-weighted) and DSO 19 days. The blended in-place rate held at $126/kW/mo after 2.5–3.0% escalators were applied across the book.

Key developments: sale process launched, PHX II on schedule but its contingency is spent

Sale process. On 19 November 2025 the Board authorized management to evaluate strategic alternatives, including interviewing financial advisors, without committing the company to a transaction. By written consent on 12 February 2026 it engaged an exclusive financial advisor for a potential sale of 100% of the equity, and at a special meeting on 28 April 2026 it authorized the sale process itself. The process launched in May 2026; indications of interest were due on 23 July 2026, with management meetings, final bids and signing to follow in H2 2026. The RNO I ground lease needs landlord consent on a change of control (consent was obtained in 2019).

PHX II (60 MW, Mesa). $412M of the $618M budget (67%) was spent by 31 March. Energization is set for October 2026 and first delivery for November 2026. The project is 70% pre-leased, and two hyperscale proposals for the remaining 18 MW are outstanding. The owner contingency is used up: change orders of $11.8M cut it from $14.0M to $2.2M, $4.0M has been spent, leaving ($1.8M) with $206M of work to go. A disputed $4.6M HVAC claim is outside the budget; the related lien is expected to settle in H2 2026 within the $1.2M accrual.

ATL II (36 MW, Atlanta). $96M of the $370M budget was spent; steel erection is underway and June 2027 delivery is unchanged. No senior leaders have left during the process.

Capital deployment was funded by operating cash flow and construction draws

Development and maintenance capex was $75.7M in the quarter, funded by $38.1M of operating cash flow and $65.0M of construction facility draws, which lifted facilities drawn to $485.0M. The company paid $19.4M of distributions to members and ended with $91.2M of cash. Net debt was $1,543.8M, 6.6x LTM adjusted EBITDA of $235.6M (management-definition adjusted EBITDA and net debt at 31 March 2026, not a buyer diligence figure), inside the 7.5x covenant maximum. The $480M left to spend on PHX II and ATL II exceeds the $115M of undrawn construction facilities by $365M, which must come from operating cash flow or new capital.

Valuation basis: independent campus appraisals, illustrative

The data room holds no Fund IV carrying value, so this letter uses an illustrative basis that can be traced line by line in the table below. Independent as-is appraisals value the six operating campuses, the buildings only, at $4,095M at 31 March 2026. We add development work in progress at book cost of $508M (PHX II and ATL II, not appraised) and deduct net debt of $1,543.8M, giving an equity value of $3,059M. Fund IV's 62.0% fully diluted share of that is $1,897M. Because the Class B profits interests share only in value above their distribution thresholds, a further $70M accrues to Fund IV, giving $1,967M, or 64.3% of equity. That is 4.6x invested capital of $425M (62/70 of the $480M invested in September 2019), before distributions. On the campuses alone, with no credit for work in progress, equity is $2,551M and Fund IV's share $1,652M (3.9x). The sale process, not the appraisals, will set realized value.

Valuation bridge, 31 March 2026 (US$ millions, illustrative)

| Line | Incl. WIP at cost | Campuses only |
| --- | --- | --- |
| Appraised operating campuses, as is (buildings only) | 4,095.0 | 4,095.0 |
| Plus: development work in progress at cost | 508.0 | n/a |
| Less: net debt at 31 March 2026 | (1,543.8) | (1,543.8) |
| Equity value, 100% | 3,059.2 | 2,551.2 |
| Fund IV at 62.0% fully diluted | 1,896.7 | 1,581.7 |
| Plus: Fund IV share of Class B value below thresholds | 70.5 | 70.5 |
| Fund IV share of equity value | 1,967.2 | 1,652.2 |
| Fund IV value / invested capital of $425.1M | 4.6x | 3.9x |

Risks we are monitoring: three diligence findings could weigh on bids

Contracted term. The executed hyperscale leases expire between 2028 and 2032, while the rent roll and lease abstracts show terms re-dated to 2034 to 2037 with no amendment in the data room. On executed terms the portfolio WALT is about 4.0 years, against the 6.9 years the board materials present.

Power cost recovery. Interval data put FY25 utility cost at about $92.4M against $84.2M billed to tenants, so roughly $8.2M a year of power cost may not be recovered, although the accounts book power cost equal to reimbursements.

Development cost and funding. PHX II has no owner contingency left with $206M of work to complete, and $365M of the remaining capacity-in-flight spend is not covered by committed construction facilities.

Outlook: the FY26 budget is weighted to PHX II deliveries late in the year

The Board-approved FY26 budget calls for revenue of $486M, NOI of $293M and adjusted EBITDA of $272M, including a partial-year contribution from PHX II from November 2026. Q1 delivered 23.3% of budgeted revenue and 22.8% of budgeted EBITDA, in line with a plan weighted to the fourth quarter. The budget targets 250 MW commissioned and 232 MW leased by year end, with $420M of development capex. Our priorities with management are PHX II energization and delivery, leasing the remaining 18 MW, a funding plan for capacity in flight, and a well-run sale process. We will report on indications of interest next quarter.

Yours sincerely,

Investor Relations, Halcyon Infrastructure Partners

Sources: Q1 FY26 board deck (10.06) pp3–6; Q1 FY26 flash report (2.07); Q1 FY26 consolidated statements (2.09); KPI dashboard Q1 FY26 (3.06); FY25 management accounts (2.05); FY26 budget (2.06); board minutes, FY25 fourth-quarter meeting (10.04) p5; board resolutions of 12 February and 28 April 2026 (10.05) pp1–2; first-round process letter (11.08) pp1–2; audited FY25 statements (2.03) p12; PHX II construction budget (4.06); campus appraisal reports (7.08) p4; cap table (1.03). Prior-quarter figures sum the monthly management accounts. Computed figures are in the LP update support workbook in this folder. Invested capital is derived pro rata to units. Contracted-term and power findings are from our earlier CIM review (models/CIM Review), based on the executed wholesale leases (Exhibit A p6) and power interval data (6.04).