## Slide 1: Ironvale beat its Q1 plan and launched a sale of 100% of the equity
Revenue of $113.0M and adjusted EBITDA of $62.0M ran ahead of budget. On the appraisal basis, Fund IV's 62% stake is worth an illustrative $1,967M, 4.6x invested capital; PHX II's owner contingency is fully used.
Key metrics vs budget and prior quarter
Metric
Q1 FY26
Budget
vs budget
Q4 FY25
vs Q4 FY25
Revenue ($M)
113.0
111.5
+1.3%
104.4
+8.2%
NOI ($M)
67.5
66.8
+1.0%
64.2
+5.2%
Adjusted EBITDA ($M)
62.0
61.2
+1.3%
57.7
+7.5%
Adj. EBITDA margin
54.9%
54.9%
0.0pp
55.2%
(0.3pp)
Leased MW
202.2
201.0
+1.2 MW
200.7
+1.6 MW
Occupancy
91.9%
91.4%
+0.5pp
91.2%
+0.7pp
Net debt / LTM EBITDA*
6.6x
n/a
n/a
6.6x
Flat
Key developments and capital deployment
On track
PHX II: $412M of $618M spent; energization Oct 2026, first delivery Nov 2026; 70% pre-leased, 18 MW in negotiation
Watch
PHX II owner contingency at ($1.8M) after $11.8M of change orders, with $206M of work still to complete
Launched
Sale of 100% of the equity launched May 2026; indications of interest due July 2026, signing targeted H2 2026
Deployed
Q1 capex $75.7M, funded by $65.0M construction draws and operating cash; $19.4M distributed; leverage 6.6x vs 7.5x covenant
Watch
Funding: $480M left to spend on PHX II and ATL II against $115M of undrawn facilities, a $365M gap
Value bridge to Fund IV's share ($M, illustrative)
4.6x
Fund IV value / invested capital of $425M
$3,059M
Equity, 100%: 4,095 campuses + 508 WIP less 1,544 net debt
Outlook: FY26 budget is weighted to Q4
Budget: revenue $486M, NOI $293M, adj. EBITDA $272M
Q1 delivered 23.3% of revenue and 22.8% of EBITDA budget
Year end: 250 MW commissioned, 232 MW leased
PHX II partial-year revenue from November 2026
Illustrative: Ironvale Digital Infrastructure is a fictional company (PE Bench). *Net debt at 31-Mar-26 / LTM adjusted EBITDA, management definition; not a buyer diligence figure. Bridge: campus appraisals at 31-Mar-26 (buildings only) + development WIP at cost - net debt = equity $3,059M; Fund IV 62.0% = $1,897M + $70M Class B value below thresholds = $1,967M (campuses only: $1,652M, 3.9x). Not a fund mark; invested capital = 62/70 of $480M (2019). Sources: Q1 FY26 flash report; FY25 management accounts; KPI dashboard; Q1 FY26 statements; Audited FS FY25 p12; board deck Q1 FY26 p3, p5, p6; PHX II budget; appraisal reports p4; cap table; FY26 budget.
Chart: 
| Campuses | Dev. WIP | Net debt | Class B | Other A | Fund IV
Base | 0 | 4095 | 3059 | 2887 | 1967 | 0
Step ($M) | 4095 | 508 | 1544 | 172 | 920 | 1967
Label | 0 | 0 | 0 | 260 | 0 | 0