## Diligence Log
Cedar Fork Commerce Park (illustrative) - Diligence Log
One row per open or material item. Due dates run from the PSA diligence period expiry or the 12/15/2026 closing (inputs below). Values link to the Exposure sheet; each row names its source document.
INPUTS
Target closing date (Offering Memorandum) |  |  |  | 2026-12-15
PSA diligence period expiry (assumed until the PSA is signed) |  |  |  | 2026-11-20
Estoppel window: maximum age at closing in days (PSA and lender set; 30 to 45 typical) |  |  |  | 30
Estoppels must be dated on or after |  |  |  | 2026-11-15
Log # | Checklist ref | Workstream | Item | Status | Owner | What the document says (source) | Value at stake ($) | Unit | Still open | Question or request to the seller | Due against | Days before | Due date
L-01 | TTL-01 | Title | Commitment status and proposed insured | Open | Counsel | Fee simple vested in Cedar Fork Industrial Partners LP; proposed insured and amount 'to be determined'; commitment lapses if B-I requirements are not met within six months of 8/20/2026 (Title commitment GF 26-118402, Kessler Bluff Title Company, Schedule A). |  |  | Commitment does not name the buyer or the purchase price. | None for the seller; counsel asks Kessler Bluff Title Company for an updated commitment naming the buyer at the purchase price. | DD expiry | 10 | 2026-11-10
L-02 | TTL-02 | Title | Legal description | Open | Counsel | Schedule A describes 19.6 acres only by reference to an unnamed recorded plat; the CAD notice describes Lot 1, Block A, Cedar Fork Commerce Park Addition (Title commitment Schedule A; Denton CAD 2026 notice; survey report Sec. 3.1). |  |  | No recordable description ties the commitment, survey and tax parcel together. | Confirm the plat name and recording data for Lot 1, Block A, Cedar Fork Commerce Park Addition. | DD expiry | 10 | 2026-11-10
L-03 | TTL-03 | Title | Monetary liens and payoffs | Closing condition | Seller | Requirement 5: release of any deed of trust, lien or monetary encumbrance of record, or evidence none exists (Title commitment Schedule B-I). |  |  | Existing deeds of trust and liens are not identified. | List every deed of trust and lien of record with lender contacts, and confirm payoff letters and releases at closing. | DD expiry | 10 | 2026-11-10
L-04 | TTL-05 | Title | Survey exception (B-II item 3) | Open | Counsel | Item 3 is the general area and boundary exception; requirement 7 allows amendment on an acceptable survey; the survey lists it only as a survey matter (Title commitment B-II and B-I; survey report Sec. 5). |  |  | Survey does not yet support amending item 3 to 'shortages in area'. | Agree that the updated survey will be delivered in time to amend item 3. | DD expiry | 5 | 2026-11-15
L-05 | TTL-07 | Title | Plat easements and setback lines (B-II items 5 and 6) | Open | Seller | Items 5 and 6 except all matters on the recorded plat; the plat is not in the room and no recording data is given (Title commitment B-II). |  |  | Platted easements and setbacks are unknown. | Provide the recorded plat with volume and page or instrument number. | DD expiry | 15 | 2026-11-05
L-06 | TTL-08 | Title | Easements 'of record' (B-II items 7, 8, 10, 11, 12) | Open | Seller | Water, electric, gas, telecom and sanitary sewer easements are listed only as 'of record', with no grantee, recording data or location (Title commitment B-II). |  |  | Five easement instruments are missing and unplotted. | Provide the recorded instruments for each of the five easements. | DD expiry | 15 | 2026-11-05
L-07 | TTL-09 | Title | 30-foot drainage and utility easement under the Building D truck court (B-II item 9) | Closing condition | Seller | Easement Vol. 4417, Pg. 212 crosses the Building D truck court and the grantee may remove improvements; all 14 striped Building D trailer stalls lie inside it (Title commitment B-II item 9; survey report Sec. 3.3). |  |  | Grantee could remove paving and 14 of the 24 marketed trailer stalls. | Provide the recorded instrument and obtain the grantee's recordable consent to the paving and stalls, with restoration at its cost, or title affirmative coverage. | Closing | 10 | 2026-12-05
L-08 | SRV-01 | Survey | Survey certification | Open | Seller | Certified only to Cedar Fork Industrial Partners LP and Kessler Bluff Title Company (Survey report, surveyor's certification). |  |  | Buyer and lender cannot rely on the survey. | Have North Texas Land Surveying recertify to the buyer, its lender and Kessler Bluff Title Company with a current field date. | DD expiry | 10 | 2026-11-10
L-09 | SRV-02 | Survey | Survey plat | Open | Seller | Only the surveyor's report is in the room; it says it is to be read with the plat dated 8/28/2026 (Survey report). |  |  | Plat not delivered. | Deliver the signed and sealed plat in PDF and CAD. | DD expiry | 15 | 2026-11-05
L-10 | SRV-03 | Survey | Table A scope | Open | Consultant | Table A items 2, 3, 4, 6(a), 7(b)(1), 8 and 9 only (Survey report, surveyor's certification). |  |  | Items 1, 6(b), 7(a), 7(c), 11 and 13 are missing. | Agree that the surveyor may expand the Table A scope for the buyer and lender. | DD expiry | 10 | 2026-11-10
L-11 | SRV-04 | Survey | Plotting of record easements | Open | Consultant | B-II items 4 to 8 and 10 to 12 are 'Listed in the title commitment', not located; the surveyor did no independent records search (Survey report Sec. 5 and 7). |  |  | Eight of 12 exceptions are unlocated. | None for the seller beyond TTL-07 and TTL-08; surveyor plots each easement once the instruments arrive. | DD expiry | 5 | 2026-11-15
L-12 | SRV-05 | Survey | Encroachments, access and boundary | Open | Consultant | No statement on encroachments, gaps, contiguity or access to Cedar Fork Parkway, and no metes-and-bounds description (Survey report). |  |  | Survey cannot support the item 3 amendment or access endorsements. | None for the seller; surveyor adds the statements and a metes-and-bounds description. | DD expiry | 5 | 2026-11-15
L-13 | ZON-02 | Zoning | C-100 outdoor storage yard (legal nonconforming) | Open | Seller | Yard behind Building C is legal nonconforming; the right is lost after 12 months of non-use or if the building is more than 50% destroyed (City of Lewisville zoning verification letter, 7/30/2026; C-100 lease Sec. 4.6). |  |  | Continuous use since the 2015 rezoning is unconfirmed. | Confirm the yard has been used continuously since 2015 and provide any City correspondence about it. | DD expiry | 15 | 2026-11-05
L-14 | ZON-03 | Zoning | Site standards, certificates of occupancy, permits and code cases | Open | Consultant | The zoning letter excludes code compliance, certificates of occupancy, open permits, code cases and site standards such as parking (Zoning verification letter Sec. 1.2). |  |  | Parking for 398 spaces, setbacks, COs and code status are unverified. | Provide certificates of occupancy for every suite and any open permits or code notices. | DD expiry | 10 | 2026-11-10
L-15 | ENV-01 | Environmental | Building E underground fuel tank (REC) | Open | Consultant | 1,000-gallon underground fuel tank from a 1990s fleet maintenance use at Building E, no TCEQ closure record; Phase II recommended at $18,000 to $25,000 (Phase I ESA, Trinity Environmental Group, 8/15/2026, Sec. 1 and 8). | 25000 | Phase II | Tank presence and any release are unknown; remediation cost is unknown. | Grant site access for a Phase II and provide any tank removal, registration or closure records. | DD expiry | 15 | 2026-11-05
L-16 | ENV-02 | Environmental | Phase I reliance and buyer user status | Open | Consultant | Prepared for the seller; reliance by others needs Trinity's written authorization; viable 180 days from the earliest component date (Phase I ESA Sec. 2.5 and 2.6). |  |  | Buyer and lender have no reliance. | Authorize Trinity to issue a reliance letter to the buyer and its lender. | DD expiry | 10 | 2026-11-10
L-17 | PHY-01 | Physical condition | Building C roof | Price item | Seller | Original 2001 built-up roof with active leaks; replace in Years 1-2 at $612,000 (Property condition assessment, Halcyon, 8/22/2026, Table 1). | 612000 | total | Not in the OM's $150,000 roof budget; not recoverable from tenants. | Replace the Building C roof before closing or credit $612,000; provide the leak and repair history. | DD expiry | 10 | 2026-11-10
L-18 | PHY-02 | Physical condition | Paving at Buildings D to F | Price item | Buyer | Mill and overlay of parking and truck court paving at Buildings D-F in Year 3, $185,000 (PCA Table 1). | 185000 | total | Not in the OM capital plan. | Provide paving maintenance history and any contractor bids. | DD expiry | 15 | 2026-11-05
L-19 | PHY-03 | Physical condition | Rooftop HVAC units | Open | Seller | Nine RTUs past their useful life; replace over Years 1-5 at $126,000; leases make tenants maintain HVAC but do not assign replacement (PCA Table 1; leases Sec. 5.1). | 126000 | total | Replacement responsibility is unclear. | Identify the nine RTUs, the suites they serve and their service contracts; confirm who replaces them under the leases. | DD expiry | 15 | 2026-11-05
L-20 | PHY-04 | Physical condition | PCA reliance | Open | Consultant | Prepared for the seller; others rely only under a written reliance letter; not a code or accessibility review (PCA Sec. 2 and 7). |  |  | Buyer and lender have no reliance. | Authorize Halcyon to issue a reliance letter to the buyer and its lender. | DD expiry | 10 | 2026-11-10
L-21 | LSE-01 | Leases and estoppels | Rent roll errors: C-300 area and C-100 step | Open | Seller | C-300 remeasured to 9,200 SF from 3/1/2025 (rent $132,020, not $140,630); C-100's $13.10/SF step starts 11/1/2026 (C-300 remeasurement letter; C-100 lease; estoppels). C-100 is timing only. | 14082 | a year | Seller rent roll still carries 9,800 SF and the early C-100 step. | Deliver a corrected rent roll, certified at closing. | DD expiry | 10 | 2026-11-10
L-22 | LSE-02 | Leases and estoppels | F-300 Prairie Dental Lab: no executed lease | Closing condition | Seller | Lease expired 5/31/2026 with no renewal option; the extension is an unsigned draft dated 5/12/2026; tenant pays $8,387.50 a month; no estoppel (F-300 lease; draft first amendment; T12). | 100650 | a year | No executed lease supports the $100,650 on the rent roll. | Deliver the executed F-300 amendment and an F-300 estoppel, or confirm the tenant is month-to-month. | Closing | 10 | 2026-12-05
L-23 | LSE-03 | Leases and estoppels | B-200 free rent | Price item | Seller | Base rent abated August 2026 through January 2027; additional rent payable (B-200 lease Sec. 2.5; B-200 estoppel). | 17283.87 | credit | Remaining free rent after closing is owed to the buyer. | Confirm the free-rent credit at closing, recomputed on the actual closing date. | Closing | 5 | 2026-12-10
L-24 | LSE-05 | Leases and estoppels | C-200 unfunded TI and offset claim | Closing condition | Seller | Landlord has not paid $38,500 of the $60,000 TI allowance; tenant claims a right to offset it against rent (C-200 estoppel, 9/24/2026, paragraphs 7 and 8). | 38500 | credit | Offset exception must be cleared before closing. | Fund the $38,500 before closing and deliver a clean C-200 estoppel, or credit $38,500 at closing. | Closing | 10 | 2026-12-05
L-25 | LSE-06 | Leases and estoppels | Missing estoppels: C-400 and F-300 | Closing condition | Seller | 15 of 17 estoppels returned; C-400 Lakeview Auto Glass and F-300 Prairie Dental Lab (17,800 SF) outstanding; leases require delivery within 10 business days of request (Estoppel tracker; leases Sec. 10.1). |  |  | Two tenants have given no estoppel. | Obtain C-400 and F-300 estoppels dated within the closing window; a seller estoppel for C-400 only as a fallback. | Closing | 10 | 2026-12-05
L-26 | LSE-07 | Leases and estoppels | Estoppel bring-down before closing | Closing condition | Seller | Returned estoppels are dated 9/8/2026 to 9/25/2026 (Estoppel tracker; estoppel certificates). At a 12/15/2026 closing, 15 of 17 will be 81 to 98 days old; most PSAs and lenders require estoppels dated within 30 to 45 days of closing. |  |  | Every estoppel must be re-issued or brought down before closing. | Re-issue or bring down all 17 estoppels, dated within the window in the inputs above, with the C-200 offset exception cleared. | Closing | 5 | 2026-12-10
L-27 | LSE-08 | Leases and estoppels | Rentable area and occupancy | Open | Seller | Leases, survey and appraisal: 248,400 SF; documented leased area 228,500 SF, 91.99% (Leases; survey report; appraisal). |  |  | Rent roll and OM use 249,000 SF and 92.01%. | Correct the area to 248,400 SF in the certified rent roll. | DD expiry | 10 | 2026-11-10
L-28 | LSE-09 | Leases and estoppels | A-100 Lone Star Cabinetry termination option | Price item | Seller | One-time right to terminate effective 6/30/2028 on notice by 9/30/2027; fee is unamortized TI and leasing commissions plus three months' base rent (A-100 first amendment, 3/15/2024; A-100 estoppel). | 1657032 | total | Fee amount and tenant intent are unknown. | Provide the A-100 TI and leasing commission amortization schedule and any tenant communication about the termination right. | DD expiry | 15 | 2026-11-05
L-29 | LSE-10 | Leases and estoppels | B-100 fixed-rate renewal | Price item | Buyer | One five-year renewal at a fixed $11.25/SF, flat (B-100 lease Article 13). | 46710 | a year | OM renews B-100 at market. | Confirm whether B-100 has indicated it will renew. | DD expiry | 15 | 2026-11-05
L-30 | FIN-01 | Financials | Termination fee in in-place NOI | Price item | Buyer | T12 other income of $148,000 includes a $142,000 early termination fee from Gulf Coast Vending for B-200, booked 1/31/2026 (GL detail account 4810; T12; OM Financial Analysis). | 142000 | a year | OM in-place NOI counts a one-time fee. | Confirm the Gulf Coast Vending fee was a one-time payment with no further obligations. | DD expiry | 15 | 2026-11-05
L-31 | FIN-02 | Financials | In-place NOI and value after diligence | Price item | Buyer | OM in-place NOI $2,879,326 at a 6.00% cap on $48,000,000; diligence adjustments cut it to $2,622,594 (OM Financial Analysis; Compound diligence checklist, Exposure sheet). | 4290100 | value | Re-trade proposal not yet made. | None; the buyer sends a re-trade proposal based on adjusted NOI. | DD expiry | 5 | 2026-11-15
L-32 | FIN-03 | Financials | Roof repair add-back | Open | Seller | T12 shows $38,000 of roof repairs that the OM adds back as non-recurring; the PCA reports the Building C roof still leaking (T12; OM; PCA). | 38000 | a year | Unclear whether repairs were billed back to tenants. | Provide roof repair invoices and the 2025-2026 CAM billing showing whether they were recovered. | DD expiry | 15 | 2026-11-05
L-33 | FIN-04 | Financials | Appraisal | Price item | Lender | As-is value $46,200,000 as of 9/1/2026, NOI $2,656,500 at 5.75%; seller is the only intended user (Appraisal, Lonestar Valuation Group). | 1800000 | value | Ask is above the appraised value; buyer and lender cannot rely on it. | None for the seller; the lender orders its own appraisal. | DD expiry | 10 | 2026-11-10
L-34 | FIN-05 | Financials | Real estate tax reassessment | Price item | Consultant | 2026 appraised value $28,400,000 at 2.25%: estimated taxes $639,000; OM holds that value grown 2% a year (Denton CAD 2026 notice; OM Cash Flow Assumptions). | 441000 | a year | Taxes on a $48.0M value are not underwritten in the OM. | Provide the 2024-2026 protest history and any CAD correspondence. | DD expiry | 15 | 2026-11-05
L-35 | FIN-06 | Financials | Tax bills and certificates | Open | Seller | T12 taxes equal the CAD estimate of $639,000, not an issued bill (T12; Denton CAD 2026 notice). |  |  | No tax bills or certificates. | Provide 2024-2026 tax bills and order tax certificates for closing. | DD expiry | 15 | 2026-11-05
L-36 | FIN-07 | Financials | CAM reconciliations and budget | Open | Seller | T12 recoveries of $930,770 against $1,078,668 of taxes, insurance and CAM; no reconciliation in the room (T12). |  |  | Recovery billing, caps and collections are unverified. | Provide 2024 and 2025 CAM reconciliations, 2026 estimates and the 2026 budget. | DD expiry | 15 | 2026-11-05
L-37 | FIN-08 | Financials | Tenant credit, receivables and operating history | Open | Seller | The room holds only the T12; no lease has a guarantor (T12; leases). |  |  | No aged receivables, tenant financials or prior-year statements. | Provide aged receivables, 2024-2025 operating statements and financials for A-100, B-100 and F-100. | DD expiry | 15 | 2026-11-05
L-38 | FIN-10 | Financials | Service contracts and management agreement | Open | Seller | No service, maintenance or management contracts in the room. |  |  | Contracts to assume or terminate are unknown. | Provide all service, maintenance and management contracts with their termination terms. | DD expiry | 15 | 2026-11-05
L-39 | INS-01 | Insurance and flood | Flood zone | Open | Consultant | About 0.6 acres of the Building F parking field lies in Zone AE (FIRM 48121C0410G); the OM and insurance certificate say the whole site is Zone X (Survey report Sec. 3.4; appraisal Sec. 3.1; OM; certificate of insurance). |  |  | Whether any building is in the AE area is unconfirmed. | Provide any flood determination or elevation certificate on file. | DD expiry | 10 | 2026-11-10
L-40 | INS-02 | Insurance and flood | Flood insurance | Open | Buyer | Flood not covered; site described as Zone X (Certificate of property insurance, Brazos Mutual, 3/1/2026). |  |  | No flood quote. | Provide any flood claims history. | DD expiry | 10 | 2026-11-10
L-41 | INS-03 | Insurance and flood | Buyer insurance at closing | Closing condition | Buyer | Seller's policy runs 3/1/2026 to 3/1/2027 with $41,500,000 on buildings and $104,328 premium (Certificate of property insurance). |  |  | Buyer coverage must be bound effective at closing. | Provide the current policy and any replacement cost valuation. | Closing | 5 | 2026-12-10
L-42 | INS-04 | Insurance and flood | Loss runs | Open | Seller | Not in the room; the Building C roof leaks may have produced claims. |  |  | No claims history. | Provide five years of loss runs. | DD expiry | 15 | 2026-11-05
L-43 | INS-05 | Insurance and flood | Tenant insurance certificates | Open | Seller | Leases require tenant liability policies naming the landlord, its manager and lender as additional insureds; no certificates in the room (Leases Sec. 7.2). |  |  | Tenant coverage is unverified. | Provide current certificates of insurance for every tenant. | DD expiry | 15 | 2026-11-05
L-44 | CLS-01 | Closing deliverables | Purchase agreement terms | Open | Counsel | No PSA in the room; the OM targets a 12/15/2026 closing (OM Offering Terms). |  |  | Diligence period, objection deadline and estoppel window are not fixed. | Agree the PSA, including the diligence period, title objection deadline, a 30 to 45 day estoppel window and the closing conditions in this log. | DD expiry | 25 | 2026-10-26
L-45 | CLS-02 | Closing deliverables | Deed, bill of sale and assignments | Closing condition | Counsel | Requirement 3: a deed from the seller to the proposed insured, executed and recorded (Title commitment Schedule B-I). |  |  | Conveyance documents not drafted. | Circulate drafts of the special warranty deed, bill of sale and assignments. | Closing | 10 | 2026-12-05
L-46 | CLS-03 | Closing deliverables | Seller authority, good standing and owner's affidavit | Closing condition | Seller | Requirements 4 and 6: evidence of the seller's existence, good standing and signing authority, and an owner's affidavit (Title commitment Schedule B-I). |  |  | Not yet delivered; C-200 lien waivers needed. | Provide formation and authority documents, good standing, and the owner's affidavit with C-200 contractor lien waivers. | Closing | 10 | 2026-12-05
L-47 | CLS-04 | Closing deliverables | Updated commitment, pro forma policy and recertified survey | Closing condition | Counsel | Commitment effective 8/20/2026 and survey dated 8/28/2026, both prepared for the seller (Title commitment; survey report). |  |  | Cures and recertification outstanding. | None for the seller beyond TTL and SRV items; counsel obtains the updated commitment and pro forma policy. | Closing | 10 | 2026-12-05
L-48 | CLS-05 | Closing deliverables | Certified rent roll and estoppels at closing | Closing condition | Seller | The 9/30/2026 rent roll overstates documented base rent by $114,732 (Seller rent roll; Lease Abstract and Rent Roll Reconciliation). |  |  | Corrected rent roll and fresh estoppels required at closing. | Certify a corrected rent roll at closing and deliver all estoppels dated within the closing window. | Closing | 5 | 2026-12-10
L-49 | CLS-06 | Closing deliverables | Security deposits (routine closing item) | Closing condition | Seller | Deposits per leases $226,820.83; estoppels confirm $209,227.50, leaving $17,593.33 (C-400, F-300) unconfirmed (Leases Sec. 2.4; estoppels). | 17593.33 | unconfirmed | C-400 and F-300 deposit balances are unconfirmed. | Confirm the C-400 and F-300 deposit balances and transfer or credit all deposits at closing. | Closing | 5 | 2026-12-10
L-50 | CLS-07 | Closing deliverables | 2026 tax proration (routine closing item) | Closing condition | Seller | 2026 taxes estimated at $639,000; no 2026 bill in the room (Denton CAD 2026 notice). |  |  | Proration method and actual bill outstanding. | Provide the 2026 tax bill when issued and agree the proration method. | Closing | 10 | 2026-12-05
L-51 | CLS-08 | Closing deliverables | Tenant notices, FIRPTA, warranties, keys and plans | Closing condition | Seller | Not yet delivered. |  |  | Closing deliverables outstanding. | Deliver tenant notice letters, FIRPTA certificate, roof and equipment warranties, keys, codes, plans and tenant files at closing. | Closing | 0 | 2026-12-15
L-52 | CLS-09 | Closing deliverables | SNDAs for the buyer's lender | Closing condition | Lender | Tenants must sign a lender's SNDA within 10 business days of request (Leases Article 11). |  |  | Lender SNDA forms not circulated. | Circulate lender SNDA forms to tenants with the estoppel bring-downs. | Closing | 15 | 2026-11-30
Formulas:
Due date = IF([Due against]="Closing",F6-[Days before],F7-[Days before])

## Seller Questions
Cedar Fork Commerce Park (illustrative) - Seller Questions
Questions and requests for the seller in priority order: quantified items by value at stake, then unquantified closing items. Due dates link to the Diligence Log.
# | Question or request to the seller | Log # | Value at stake ($) | Unit | Due date
1 | Provide the A-100 TI and leasing commission amortization schedule and any tenant communication about its 30 Jun 2028 termination right. | L-28 | 1657032 | rent at risk | 2026-11-05
2 | Will you replace the leaking Building C roof before closing, or credit $612,000? Please send the leak and repair history. | L-17 | 612000 | total | 2026-11-10
3 | Provide the 2024-2026 tax protest history and any CAD correspondence on value. | L-34 | 441000 | a year | 2026-11-05
4 | Provide paving maintenance history and any bids for the Buildings D-F mill and overlay. | L-18 | 185000 | total | 2026-11-05
5 | Confirm the $142,000 Gulf Coast Vending termination fee was a one-time payment with no continuing obligations. | L-30 | 142000 | a year | 2026-11-05
6 | Identify the nine RTUs past useful life, the suites they serve and their service contracts, and who replaces them under the leases. | L-19 | 126000 | total | 2026-11-05
7 | Deliver the executed F-300 amendment and an F-300 estoppel, or confirm Prairie Dental Lab is month-to-month. | L-22 | 100650 | a year | 2026-12-05
8 | Will you fund the $38,500 C-200 TI balance before closing and deliver a clean C-200 estoppel, or credit it at closing? | L-24 | 38500 | credit | 2026-12-05
9 | Provide roof repair invoices and the 2025-2026 CAM billing showing whether roof repairs were recovered from tenants. | L-32 | 38000 | a year | 2026-11-05
10 | Grant access for a Phase II at Building E and provide any tank registration, removal or TCEQ closure records. | L-15 | 25000 | Phase II; remediation unknown | 2026-11-05
11 | Confirm the C-400 and F-300 security deposit balances. | L-49 | 17593.33 | unconfirmed | 2026-12-10
12 | Confirm the B-200 free-rent credit at closing, recomputed on the actual closing date. | L-23 | 17283.87 | credit | 2026-12-10
13 | Deliver a corrected rent roll (C-300 at 9,200 SF, 248,400 SF total), certified at closing. | L-21, L-27 | 14082 | a year | 2026-11-10
14 | Provide the Vol. 4417, Pg. 212 easement and obtain the grantee's recordable consent to the Building D paving and 14 trailer stalls, or title affirmative coverage. | L-07 |  | not quantified | 2026-12-05
15 | Obtain C-400 and F-300 estoppels, and have all 17 tenants re-issue or bring down estoppels dated within 30 to 45 days of closing. | L-25, L-26 |  | closing condition | 2026-12-05
16 | List every deed of trust and lien of record and confirm payoffs and releases at closing. | L-03 |  | closing condition | 2026-11-10
17 | Provide the recorded plat, the five easement instruments and the signed survey plat, and have the survey recertified to us, our lender and Kessler Bluff Title Company. | L-05, L-06, L-08, L-09 |  | not quantified | 2026-11-05
18 | Provide certificates of occupancy, any open permits or code notices, and confirm continuous use of the C-100 storage yard since 2015. | L-14, L-13 |  | not quantified | 2026-11-05
19 | Provide CAM reconciliations, tax bills, aged receivables, prior-year statements, contracts, loss runs and tenant insurance certificates. | L-36, L-35, L-37, L-38, L-42, L-43 |  | not quantified | 2026-11-05

## Summary
Cedar Fork Commerce Park (illustrative) - Due Diligence Summary
Status counts read from the Checklist; key exposures read from the Exposure sheet.
STATUS BY CATEGORY | Items | Clear | Issue | Missing
Title | 9 | 3 | 3 | 3
Survey | 6 | 1 | 4 | 1
Zoning | 3 | 1 | 1 | 1
Environmental | 3 | 1 | 2 | 0
Physical condition | 5 | 1 | 4 | 0
Leases and estoppels | 11 | 2 | 8 | 1
Financials | 10 | 1 | 5 | 4
Insurance and flood | 5 | 1 | 2 | 2
Closing deliverables | 9 | 0 | 1 | 8
Total | 61 | 11 | 30 | 20
ITEMS BY ACTION | Items
Price adjustment | 8
Closing condition | 16
Request from seller | 21
Order a report | 8
None required | 8
Total | 61
KEY DOLLAR EXPOSURES | Amount ($) | Basis
Asking price above appraised value | 1800000 | Appraisal $46.2M as of 9/1/2026 (FIN-04)
OM in-place NOI overstatement | 256732 | Annual: rent roll variances and one-time termination fee (FIN-02)
Value effect of NOI overstatement | -4290100 | At the OM's 6.00% cap rate (FIN-02)
PCA capital above OM roof budget | 773000 | PCA $923,000 against $150,000 OM roof capital (PHY-01 to PHY-03)
Building C roof replacement | 612000 | One-time, not recoverable from tenants (PHY-01)
Real estate tax increase on reassessment | 441000 | Annual, at the asking price (FIN-05)
A-100 base rent after termination date | 1657032 | 7/1/2028 to 6/30/2032, if exercised (LSE-09)
Phase II investigation, high estimate | 25000 | Remediation cost unknown (ENV-01)
Credits from diligence findings | 55783.87 | C-200 unfunded TI and B-200 free rent (LSE-03, LSE-05); deposits and 2026 tax proration are routine closing items
Indicative value after diligence findings | 43097900 | Adjusted NOI at 6.00% less Building C roof; judgment, not an appraisal
ROUTINE CLOSING ITEMS (NOT DILIGENCE FINDINGS) | Amount ($) | Basis
Tenant security deposits | 226820.83 | Transfer or credit per the leases; $17,593.33 (C-400, F-300) not yet confirmed by estoppel (CLS-06)
2026 real estate tax proration, estimate | 609238.3562 | CAD estimate of $639,000 prorated to closing; trued up on the actual bill (CLS-07)
Routine closing items | 836059.1862
DILIGENCE LOG | Items | Due by DD expiry | Due by closing
Seller | 29 | 18 | 11
Buyer | 6 | 5 | 1
Counsel | 6 | 4 | 2
Lender | 2 | 1 | 1
Consultant | 9 | 9 | 0
Total | 52 | 37 | 15
Of which closing conditions | 15

## Checklist
Cedar Fork Commerce Park (illustrative) - Real Estate Due Diligence Checklist
One row per diligence item. Documents are in the Cedar Fork Data Room unless marked Missing; the Lease Abstract and Rent Roll Reconciliation is our earlier work in Buyer Diligence. Dollar exposures link to the Exposure sheet.
Ref | Category | Diligence item | Document in data room | Status | What the document says | Conflict with OM or other documents | Dollar exposure ($) | Exposure basis | Action | Next step
TITLE
TTL-01 | Title | Vesting, estate and commitment status | Title Commitment GF 26-118402 (Kessler Bluff Title Company, effective 8/20/2026) | Clear | Fee simple title vested in Cedar Fork Industrial Partners LP. Owner's Policy to be issued; proposed insured and amount 'to be determined'. The commitment terminates if the Schedule B-I requirements are not met within six months of the Commitment Date. | None. Vesting matches the seller named in the OM. |  |  | Request from seller | Title company to name the buyer entity and the purchase price, and issue an updated commitment and pro forma owner's policy before the title objection deadline.
TTL-02 | Title | Legal description | Title Commitment, Schedule A; Denton CAD 2026 Notice of Appraised Value; ALTA/NSPS Survey Report | Issue | Schedule A describes 19.6 acres only 'as more particularly described in the recorded plat of the Land', with no plat name or recording data. The survey adopts the Schedule A description. The CAD notice describes the parcel as Lot 1, Block A, Cedar Fork Commerce Park Addition. | No document in the room gives a recordable description that ties the commitment, the survey and the tax parcel together. |  |  | Request from seller | Title objection: amend Schedule A to Lot 1, Block A with plat recording data; surveyor to add a metes-and-bounds description and certify it matches the record description.
TTL-03 | Title | Monetary liens (Schedule B-I, requirement 5) | Title Commitment, Schedule B-I | Missing | Requirement 5 calls for release of any deed of trust, lien or other monetary encumbrance of record, or evidence that none exists. The room has no list of existing liens or payoff information. | None. |  |  | Closing condition | Seller to identify each deed of trust and lien and deliver payoff letters and recordable releases at closing.
TTL-04 | Title | Schedule B-II items 1 and 2: taxes and tenants' rights | Title Commitment, Schedule B-II; leases; tenant estoppels | Clear | Item 1 is the standard exception for 2026 and later taxes not yet due. Item 2 covers tenants in possession as tenants only, without any right of first refusal or option to purchase. No lease in the room grants a purchase option or right of first refusal, and the estoppels certify none beyond the lease terms. | None. |  |  | None required | Accept both; 2026 taxes are prorated at closing (CLS-07).
TTL-05 | Title | Schedule B-II item 3: survey exception | Title Commitment, Schedule B-II and B-I requirement 7; ALTA/NSPS Survey Report | Issue | Item 3 is the general area, boundary and encroachment exception. Requirement 7 allows it to be amended on an acceptable ALTA/NSPS survey. The survey report lists item 3 only as a 'survey matter' and states no finding on encroachments, gaps or overlaps. | The survey as delivered does not support amending the exception. |  |  | Closing condition | Title objection: amend item 3 to 'shortages in area' on the recertified survey (buyer pays the premium).
TTL-06 | Title | Schedule B-II item 4: public rights in roads | Title Commitment, Schedule B-II; ALTA/NSPS Survey Report | Clear | Standard exception for rights of the public, the State of Texas and the City of Lewisville in any part of the land within a public road or right-of-way, including Cedar Fork Parkway. | None. The survey lists it without comment. |  |  | Request from seller | Accept, limited to dedicated right-of-way; surveyor to confirm no improvements lie within it.
TTL-07 | Title | Schedule B-II items 5 and 6: plat easements and setback lines | Missing: recorded plat | Missing | Items 5 and 6 except all easements, building setback lines, utility easements and other matters shown on the recorded plat. The plat is not in the room and the commitment gives no recording data. | The survey says only 'Listed in the title commitment', so nothing shows whether a building or truck court sits in a platted easement or over a setback line. |  |  | Request from seller | Title objection: deliver the recorded plat; limit items 5 and 6 to specific platted easements and setbacks; surveyor to plot each.
TTL-08 | Title | Schedule B-II items 7, 8, 10, 11 and 12: water, electric, gas, telecom and sanitary sewer easements 'of record' | Missing: recorded easement instruments | Missing | Each item reads only '... easement of record', with no grantee, recording reference or location. No copies are in the room, and the surveyor did not search the public records or plot them. | The survey says only 'Listed in the title commitment' for each. |  |  | Request from seller | Title objection: recording data and legible copies for each; surveyor to plot or state not plottable; delete any that do not affect the land; object to any blanket easement or one under a building.
TTL-09 | Title | Schedule B-II item 9: 30-foot drainage and utility easement, Vol. 4417, Pg. 212 | Title Commitment, Schedule B-II; ALTA/NSPS Survey Report | Issue | The easement crosses the Building D truck court and the grantee may remove improvements within it. The survey places all 14 striped Building D trailer stalls inside the easement. | The OM markets 24 trailer stalls, 14 at Building D, and does not mention the easement. |  | Not quantified: 14 of 24 trailer stalls (58%) and the Building D truck court paving | Closing condition | Title objection: copy of the instrument; seller to obtain the grantee's recordable consent letting the paving and stalls remain, with restoration at the grantee's cost, or title to insure over removal; otherwise price adjustment.
SURVEY
SRV-01 | Survey | Certification and parties | ALTA/NSPS Survey Report (North Texas Land Surveying, plat and report dated 8/28/2026) | Issue | Certified only to Cedar Fork Industrial Partners LP and Kessler Bluff Title Company. | Buyer and buyer's lender cannot rely on it. |  |  | Request from seller | Surveyor to recertify to buyer, buyer's lender and the title company, with a current field date.
SRV-02 | Survey | Survey plat | Missing: signed and sealed survey plat | Missing | Only the surveyor's report is in the room; the report says it is to be read with the plat dated 8/28/2026. | None. |  |  | Request from seller | Deliver the signed and sealed plat in PDF and CAD.
SRV-03 | Survey | Table A scope | ALTA/NSPS Survey Report, surveyor's certification | Issue | Covers Table A items 2, 3, 4, 6(a), 7(b)(1), 8 and 9 only. | Without monuments (1), zoning setbacks and height (6(b)), building dimensions and height (7(a), 7(c)), utilities (11) and adjoining owners (13), the survey cannot support zoning, access or utility endorsements. |  |  | Order a report | Expand the scope to add those items and any offsite easements.
SRV-04 | Survey | Plotting of Schedule B-II easements | ALTA/NSPS Survey Report, Section 5 | Issue | Items 4 to 8 and 10 to 12 are marked 'Listed in the title commitment' instead of being located. Only item 9 is plotted. The surveyor did not perform an independent search of the public records. | The location of 8 of the 12 Schedule B-II items is unknown. |  |  | Order a report | Surveyor to plot each easement once the instruments are produced, or state that it is blanket, not plottable or does not affect the land.
SRV-05 | Survey | Encroachments, access and boundary | ALTA/NSPS Survey Report | Issue | The report makes no statement on encroachments, gaps or gores, contiguity, or direct access to Cedar Fork Parkway, and gives no metes-and-bounds description. | These statements are needed to amend B-II item 3 and for access and contiguity endorsements. |  |  | Request from seller | Surveyor to add a metes-and-bounds description and express statements on encroachments, access and gaps; show the fenced C-100 storage yard against boundary and setback lines.
SRV-06 | Survey | Building area, parking and trailer stalls | ALTA/NSPS Survey Report; Offering Memorandum; seller rent roll | Clear | Six buildings, 248,400 SF; 398 car parking spaces and 24 trailer stalls (14 at Building D, 10 at Building F). | Matches the OM building area and parking. The seller rent roll totals 249,000 SF (LSE-08). |  |  | None required | Use 248,400 SF for price per SF and recovery shares.
ZONING
ZON-01 | Zoning | Zoning district and use | Zoning Verification Letter (City of Lewisville, 7/30/2026) | Clear | Zoned LI-2 (rezoned 2015). The current multi-tenant light industrial / flex uses of Buildings A through F conform to the district. | None. Matches the OM. |  |  | None required | None.
ZON-02 | Zoning | C-100 outdoor storage yard: legal nonconforming use | Zoning Verification Letter; C-100 Brazos Fire Protection Lease (Sec. 4.6) | Issue | The fenced yard behind Building C used by C-100 is legal nonconforming; the right is lost if the use stops for 12 months or the building is more than 50% destroyed. The C-100 lease grants exclusive use of the yard for the term. | The OM does not mention it. The right can be lost through a C-100 vacancy or a major casualty. |  |  | Request from seller | Seller to confirm continuous use since 2015; keep the yard in use through any C-100 re-leasing; check ordinance-or-law coverage.
ZON-03 | Zoning | Site standards, certificates of occupancy, open permits and code cases | Missing: zoning report, certificates of occupancy, City permit and code records | Missing | The zoning letter does not cover code compliance, certificates of occupancy, open permits, code enforcement cases, platting, or site standards such as setbacks, parking, landscaping or lot coverage. | Parking compliance for 398 spaces on 248,400 SF is unverified. |  |  | Order a report | Order a zoning report (parking, setbacks, coverage, CO search, open permits, code cases); seller to deliver suite certificates of occupancy.
ENVIRONMENTAL
ENV-01 | Environmental | Recognized environmental condition: Building E underground fuel tank | Phase I ESA (Trinity Environmental Group, 8/15/2026) | Issue | REC: a 1,000-gallon underground fuel tank from a 1990s fleet maintenance use at Building E, with no closure record with TCEQ. Trinity recommends a Phase II subsurface investigation ($18,000 to $25,000). | The OM does not mention the tank or any environmental condition. | 25000 | Phase II cost, high estimate; remediation cost unknown until the Phase II | Order a report | Order the Phase II before the diligence period ends. If a tank or release is confirmed: seller removal and TCEQ closure before closing, an escrow, or a price adjustment.
ENV-02 | Environmental | Phase I reliance and buyer user status | Phase I ESA, Sections 2.5 and 2.6 | Issue | The User is the seller; reliance by any other party requires Trinity's written authorization. The report is presumed viable for 180 days from the earliest component date. | Buyer has no reliance and has not made its own user inquiries. |  |  | Order a report | Reliance letter for buyer and lender; buyer user questionnaire; update the report if components will be over 180 days old at closing.
ENV-03 | Environmental | Tenant hazardous materials use | Phase I ESA, Section 6; leases (Sec. 4.3) | Clear | Products observed in quantities consistent with light industrial use; no releases observed. Leases allow only customary quantities handled in compliance with law, with a tenant indemnity that survives. | None. Asbestos, lead-based paint, radon and mold are outside the Phase I scope. |  |  | None required | None beyond ENV-01 and ENV-02.
PHYSICAL CONDITION
PHY-01 | Physical condition | Building C roof | Property Condition Assessment (Halcyon Building Sciences, 8/22/2026) | Issue | Original 2001 built-up roof with active leaks, at the end of its useful life. Replace in Years 1-2 at $612,000. | The OM budgets $150,000 of roof capital and calls the capital plan 'in place'. The leases exclude capital improvements from recoverable Operating Expenses, so the owner bears the cost. | 612000 | One-time capital, not recoverable from tenants | Price adjustment | Seller replaces the roof before closing or credits $612,000; request the roof leak and repair history.
PHY-02 | Physical condition | Paving at Buildings D to F | Property Condition Assessment | Issue | Mill and overlay of the parking and truck court paving serving Buildings D-F in Year 3, $185,000. | Not in the OM capital plan. Part of the Building D truck court lies in the B-II item 9 easement (TTL-09). | 185000 | One-time capital, Year 3 | Price adjustment | Carry in underwriting capital; include in the price discussion with PHY-01.
PHY-03 | Physical condition | Rooftop HVAC units | Property Condition Assessment; leases (Sec. 5.1) | Issue | Nine RTUs past their useful life; replace over Years 1-5 at $126,000. Tenants maintain the HVAC equipment serving their premises; the leases do not say who replaces it. | The OM's $0.15/SF annual reserve is the only funding. | 126000 | Capital over Years 1-5 | Request from seller | Seller to identify the units, the suites they serve and the maintenance contracts; confirm replacement responsibility under the leases.
PHY-04 | Physical condition | PCA reliance and scope | Property Condition Assessment, Sections 2 and 7 | Issue | Prepared for the seller; other parties rely only under a written reliance letter. Not a code compliance review or accessibility survey. | Buyer and lender have no reliance. |  |  | Order a report | Obtain a reliance letter, or commission the buyer's own PCA with an accessibility review.
PHY-05 | Physical condition | Roofs, structure and envelope of Buildings A, B, D, E and F | Property Condition Assessment | Clear | Roofs installed 2011 to 2019 are serviceable with no leaks observed; no structural or envelope deficiencies; no other immediate or short-term costs identified. | None. Roof dates match the OM. |  |  | None required | Request roof warranties and transfer them at closing (CLS-08).
LEASES AND ESTOPPELS
LSE-01 | Leases and estoppels | Rent roll errors: C-300 area and C-100 rent step | Leases; C-300 Remeasurement of Premises Letter (2/10/2025); estoppels; Lease Abstract and Rent Roll Reconciliation | Issue | C-300 was remeasured to 9,200 SF effective 3/1/2025, so rent is $132,020, not $140,630. C-100's $13.10/SF step starts 11/1/2026; $12.72/SF was in effect at 9/30/2026. | The seller rent roll and OM tenant roster carry C-300 at 9,800 SF and $140,630, and C-100 at $13.10/SF. | 14082 | Annual base rent; the C-100 part cures on 11/1/2026 | Request from seller | Seller corrects and certifies the rent roll; C-300 recoveries at 3.70%.
LSE-02 | Leases and estoppels | F-300 Prairie Dental Lab: no executed lease in effect | F-300 Lease (6/1/2021); F-300 First Amendment DRAFT 5/12/2026 | Issue | The lease expired 5/31/2026 with no renewal option. The extension to 5/31/2029 is an unsigned draft. The tenant has paid the draft rate of $8,387.50 a month since June 2026. No estoppel. | The rent roll and OM show a lease through 5/31/2029 at $100,650 a year. | 100650 | Annual base rent | Closing condition | Executed amendment and estoppel before closing; otherwise underwrite month-to-month and reduce the price.
LSE-03 | Leases and estoppels | B-200 free rent | B-200 Pecan Street Brewing Supply Lease (Sec. 2.5); B-200 estoppel | Issue | Base rent is abated August 2026 through January 2027; additional rent is payable. | The rent roll and OM count $136,800 as in-place base rent. | 17283.87 | Closing credit to buyer at a 12/15/2026 closing | Price adjustment | Seller credits the remaining free rent at closing, recomputed on the actual date.
LSE-04 | Leases and estoppels | B-200 tenant improvement allowance | B-200 Pecan Street Brewing Supply Lease (Sec. 6.5); B-200 estoppel, version 2 | Clear | The lease grants a $96,000 improvement allowance (Sec. 6.5). The tenant's estoppel version 2 certifies it has been paid in full, so there is no B-200 TI credit or risk. | None. The first estoppel (21 Sep 2026) was silent on the allowance. | 0 | None: paid in full per estoppel v2 | None required | None.
LSE-05 | Leases and estoppels | C-200 unfunded TI and rent offset claim | C-200 Redbird HVAC Services estoppel (9/24/2026) | Issue | Landlord has not paid $38,500 of the $60,000 TI allowance; the tenant claims the right to offset it against rent. | Not shown on the rent roll. | 38500 | Closing credit unless seller funds before closing | Closing condition | Seller funds before closing and delivers a clean C-200 estoppel, or credits $38,500.
LSE-06 | Leases and estoppels | Missing estoppels: C-400 and F-300 | Estoppel Tracker; leases (Sec. 10.1) | Missing | 15 of 17 estoppels returned. C-400 Lakeview Auto Glass and F-300 Prairie Dental Lab (17,800 SF) are outstanding. Leases require a tenant to deliver an estoppel within 10 business days of request. | None. |  |  | Closing condition | Require both estoppels; a seller estoppel for C-400 only as a fallback.
LSE-07 | Leases and estoppels | Estoppel dating | Tenant estoppel certificates dated 9/8/2026 to 9/25/2026 | Issue | Returned estoppels are dated 9/8/2026 to 9/25/2026 and run to any prospective purchaser and its lender. | At the 12/15/2026 closing, 15 of 17 will be 81 to 98 days old. Most PSAs and lenders require estoppels dated within 30 to 45 days of closing, so they must be re-issued or brought down before closing. |  |  | Closing condition | Closing condition: every tenant re-issues or brings down its estoppel, dated within 30 to 45 days of closing as the PSA and lender set; this includes a clean C-200 estoppel and first estoppels from C-400 and F-300.
LSE-08 | Leases and estoppels | Rentable area and occupancy | Seller rent roll; leases; ALTA/NSPS Survey Report; Appraisal | Issue | Leases, survey and appraisal: 248,400 SF. Documented leased area is 228,500 SF, or 91.99%. | The rent roll and OM show 249,000 SF and 92.01% leased. |  |  | Request from seller | Correct the rent roll; run price per SF and recovery shares on 248,400 SF.
LSE-09 | Leases and estoppels | A-100 Lone Star Cabinetry termination option | A-100 First Amendment to Lease (3/15/2024); A-100 estoppel | Issue | One-time right to terminate effective 6/30/2028 on notice by 9/30/2027. Fee: unamortized TI and leasing commissions plus three months' base rent ($94,926 base-rent part). | The OM says the largest tenant is 'committed through June 2032'; the rent roll omits the right. | 1657032 | Base rent after 6/30/2028 at risk | Request from seller | Get the TI and commission amortization schedule and any signal of tenant intent; underwrite the termination case.
LSE-10 | Leases and estoppels | B-100 Trinity Medical Logistics fixed-rate renewal | B-100 Trinity Medical Logistics Lease (Article 13) | Issue | One 5-year renewal at a fixed $11.25/SF, flat. | The rent roll shows '1 x 5 yrs' with no rate; the OM cash flow renews at market. | 46710 | Annual base rent against seller 2028 market rent | Price adjustment | Underwrite the B-100 renewal at $11.25/SF.
LSE-11 | Leases and estoppels | Lease form: subordination, SNDA, estoppels, purchase rights and guaranties | Leases (Articles 10, 11 and 13) | Clear | Leases are subordinate to any mortgage subject to non-disturbance; tenants must sign an SNDA and an estoppel within 10 business days of request. No lease has a purchase option or right of first refusal, and none has a guarantor. | None. |  |  | None required | Weigh the absence of guarantors in the tenant credit review (FIN-08).
FINANCIALS
FIN-01 | Financials | One-time termination fee in in-place NOI | GL Detail Other Income (account 4810); T12 Operating Statement; Offering Memorandum | Issue | T12 other income of $148,000 includes a $142,000 early termination fee paid by Gulf Coast Vending for B-200, booked 1/31/2026. | The OM's in-place NOI of $2,879,326 includes the full $148,000; the OM cash flow carries only late fees. | 142000 | Annual NOI overstatement | Price adjustment | Remove from in-place NOI (NOI bridge on the Exposure sheet).
FIN-02 | Financials | In-place NOI and value after diligence adjustments | Offering Memorandum, Financial Analysis; Lease Abstract and Rent Roll Reconciliation; GL Detail Other Income | Issue | OM in-place NOI of $2,879,326 on the $48,000,000 asking price is a 6.00% cap rate. | Removing the rent roll variances and the termination fee cuts in-place NOI by $256,732 (8.9%) to $2,622,594, a 5.46% cap rate on the asking price. | 4290100 | Value effect at the OM's 6.00% cap rate | Price adjustment | Re-trade on adjusted NOI; carry the adjustments into the acquisition model.
FIN-03 | Financials | Roof repair add-back | T12 Operating Statement (Roof Repairs); Offering Memorandum; Property Condition Assessment | Issue | The T12 shows $38,000 of roof repairs; the OM adds them back to NOI as non-recurring. | The PCA reports the Building C roof still leaking, so repairs recur until it is replaced. Roof repairs are recoverable Operating Expenses under the leases, so the net effect depends on what was billed back. | 38000 | Annual NOI until the Building C roof is replaced | Request from seller | Request roof repair invoices and the CAM reconciliation showing whether they were billed to tenants; falls away once PHY-01 is resolved.
FIN-04 | Financials | Appraisal | Appraisal (Lonestar Valuation Group, value as of 9/1/2026) | Issue | As-is leased fee value $46,200,000: NOI $2,656,500 at a 5.75% cap rate; 91.99% occupied. The seller is the only intended user. | The asking price is $1,800,000 (3.9%) above the appraised value. | 1800000 | Asking price above appraised value | Price adjustment | Use in the re-trade; the lender will order its own appraisal.
FIN-05 | Financials | Real estate tax reassessment | Denton CAD 2026 Notice of Appraised Value; Offering Memorandum, Cash Flow Assumptions | Issue | 2026 appraised value $28,400,000 at a 2.25% combined rate; estimated taxes $639,000. | The OM holds taxes on the $28.4M value grown 2% a year, against a $48.0M price and a $46.2M appraisal. | 441000 | Annual tax increase at the asking price; the owner bears about $35,330 on vacant space and NNN tenants the rest | Price adjustment | Underwrite taxes on the purchase price; tenants' occupancy cost rises and the owner pays the vacant share; retain a tax consultant.
FIN-06 | Financials | Tax bills, tax certificates and protest history | Missing: 2024-2026 tax bills, tax certificates, protest records | Missing | The T12 real estate tax expense ($639,000) equals the CAD estimate, not an issued bill. The notice says actual taxes may be higher or lower. | None. |  |  | Request from seller | Request 2024-2026 tax bills, protest history and tax certificates for closing.
FIN-07 | Financials | CAM reconciliations and operating budget | Missing: 2024 and 2025 CAM reconciliations, 2026 budget and estimates | Missing | T12 expense recoveries are $930,770 against $1,078,668 of taxes, insurance and CAM. Nothing in the room shows how recoveries were billed, capped or collected. | None. |  |  | Request from seller | Request reconciliations, 2026 estimates and budget; reconcile 2026 recoveries at closing.
FIN-08 | Financials | Tenant credit, receivables and operating history | Missing: aged receivables, tenant financial statements, 2024-2025 operating statements | Missing | The room holds only the T12. No lease has a guarantor. | None. |  |  | Request from seller | Request aged receivables and delinquency, two prior years of operating statements, and financials for A-100, B-100 and F-100.
FIN-09 | Financials | T12 base rent against the rent roll | T12 Operating Statement; Lease Abstract and Rent Roll Reconciliation | Clear | September 2026 billed base rent times 12 ($2,866,100) ties to the corrected rent roll. | None beyond LSE-01 and LSE-02. |  |  | None required | None.
FIN-10 | Financials | Service contracts and management agreement | Missing: service, maintenance and management contracts | Missing | Not in the room. | None. |  |  | Request from seller | Request all contracts; elect which to assume; seller terminates the rest at closing.
INSURANCE AND FLOOD
INS-01 | Insurance and flood | Flood zone | ALTA/NSPS Survey Report; Appraisal; Offering Memorandum; Certificate of Property Insurance | Issue | Survey and appraisal: about 0.6 acres of the Building F parking field lies in Zone AE (FIRM panel 48121C0410G); the rest of the site is Zone X. The survey plotted this graphically and says it is not a flood elevation certificate. | The OM says the entire site lies in Zone X; the insurance certificate also describes the site as Zone X. |  | Not quantified: 0.6 of 19.6 acres (3.1%) of the site | Order a report | Order a life-of-loan flood determination; confirm no building lies in the AE area; elevation certificate if a building is near it.
INS-02 | Insurance and flood | Flood insurance | Certificate of Property Insurance (Brazos Mutual, issued 3/1/2026) | Issue | Flood is not covered. | The certificate describes the site as Zone X, contrary to the survey and appraisal. |  | Premium not quantified | Order a report | Get a flood insurance quote; the lender will require coverage if any building lies in the special flood hazard area.
INS-03 | Insurance and flood | Property and liability coverage | Certificate of Property Insurance | Clear | Policy 3/1/2026 to 3/1/2027; buildings $41,500,000; general liability $1,000,000 per occurrence and $2,000,000 aggregate; annual premium $104,328. | Premium matches T12 insurance expense. The building limit is not tied to a replacement cost valuation. |  |  | Closing condition | Buyer binds its own property, liability and any flood coverage effective at closing; obtain a replacement cost valuation.
INS-04 | Insurance and flood | Loss runs | Missing: five-year loss runs | Missing | Not in the room. | Building C roof leaks may have produced claims. |  |  | Request from seller | Request five years of loss runs.
INS-05 | Insurance and flood | Tenant insurance certificates | Missing: tenant certificates of insurance | Missing | Leases require tenant liability policies naming the landlord, its property manager and its lender as additional insureds. No certificates are in the room. | None. |  |  | Request from seller | Request current certificates for all tenants; tenants to reissue naming buyer at closing.
CLOSING DELIVERABLES
CLS-01 | Closing deliverables | Purchase agreement deadlines | Missing: purchase and sale agreement | Missing | Not in the room. The OM targets a 12/15/2026 closing. | None. |  |  | Request from seller | Set the title and survey objection period, estoppel thresholds and dating, and the closing conditions in this checklist in the PSA.
CLS-02 | Closing deliverables | Deed, bill of sale and assignments | Title Commitment, Schedule B-I requirement 3 | Missing | Requirement 3: a deed from Cedar Fork Industrial Partners LP to the proposed insured, executed and recorded. Bill of sale and assignments not yet drafted. | None. |  |  | Closing condition | Special warranty deed, bill of sale, assignment and assumption of leases, and assignment of contracts, warranties and intangibles.
CLS-03 | Closing deliverables | Seller authority, good standing and owner's affidavit | Title Commitment, Schedule B-I requirements 4 and 6 | Missing | Requirements 4 and 6: evidence of the seller's existence, good standing and signing authority, and an owner's affidavit as to debts, liens and parties in possession. | None. |  |  | Closing condition | Seller delivers; affidavit and lien waivers to cover TI work at C-200.
CLS-04 | Closing deliverables | Updated title commitment, pro forma policy and recertified survey | Title Commitment (effective 8/20/2026); ALTA/NSPS Survey Report (8/28/2026) | Missing | Both were prepared for the seller; the commitment is effective 8/20/2026 and the survey is dated 8/28/2026. | None. |  |  | Closing condition | Updated commitment with the TTL-02 to TTL-09 cures; pro forma owner's policy with agreed endorsements; survey recertified (SRV-01 to SRV-05).
CLS-05 | Closing deliverables | Certified rent roll and estoppels at closing | Seller rent roll (9/30/2026); Estoppel Tracker | Missing | The 9/30/2026 rent roll overstates documented base rent by $114,732. | See LSE-01 to LSE-08. |  |  | Closing condition | Seller certifies a corrected rent roll at closing; all 17 estoppels re-issued or brought down within 30 to 45 days of closing and delivered without unresolved exceptions.
CLS-06 | Closing deliverables | Security deposits | Leases (Sec. 2.4); Lease Abstract and Rent Roll Reconciliation | Issue | Deposits per the leases total $226,820.83; estoppels confirm $209,227.50, leaving $17,593.33 (C-400, F-300) unconfirmed. Landlord may transfer deposits to a purchaser. | None. |  | Routine closing item, not a diligence finding: $226,820.83 of deposits transfer to buyer | Closing condition | Seller transfers or credits all deposits per the leases.
CLS-07 | Closing deliverables | 2026 real estate tax proration | Denton CAD 2026 Notice of Appraised Value; Offering Memorandum | Missing | No 2026 tax bill is in the room. The CAD notice estimates 2026 taxes at $639,000 and says the taxing units set 2026 rates later in the year. | None. |  | Routine closing item, not a diligence finding: estimated $609,238 credit to buyer before the tenant recovery true-up | Closing condition | Prorate 2026 taxes on the actual bill; true up tenant recoveries after closing.
CLS-08 | Closing deliverables | Tenant notices, FIRPTA, warranties, keys and plans | Missing | Missing | Not yet delivered. | None. |  |  | Closing condition | Tenant notice letters, FIRPTA certificate, roof and equipment warranties, keys and access codes, plans, tenant files.
CLS-09 | Closing deliverables | SNDAs for the buyer's lender | Leases (Article 11) | Missing | Tenants must sign a lender's SNDA in commercially reasonable form within 10 business days of request. | None. |  |  | Closing condition | If financing, circulate lender SNDA forms with the estoppel bring-downs.

## Exposure
Cedar Fork Commerce Park (illustrative) - Diligence Exposure Calculations
Dollar exposures behind the Checklist. Inputs are read from the data room and the lease reconciliation workbook; every computed figure is a formula.
INPUTS | Amount | Source
Target closing date | 2026-12-15 | Offering Memorandum, Offering Terms
Asking price | 48000000 | Offering Memorandum, Offering Terms
In-place NOI per OM | 2879326 | Offering Memorandum, Financial Analysis
In-place cap rate per OM | 6% | Offering Memorandum, Financial Analysis
Building area (SF) | 248400 | ALTA/NSPS Survey Report, Executive summary
Vacant area, B-300 and E-200 (SF) | 19900 | Offering Memorandum, Rent Roll Summary
Site area (acres) | 19.6 | ALTA/NSPS Survey Report, Executive summary
Building F parking field in flood Zone AE (acres) | 0.6 | ALTA/NSPS Survey Report, Executive summary
Trailer stalls, total | 24 | ALTA/NSPS Survey Report, Executive summary
Building D trailer stalls inside the Schedule B-II item 9 easement | 14 | ALTA/NSPS Survey Report, Executive summary
PRICE AND APPRAISAL
Appraised as-is market value, leased fee, 9/1/2026 | 46200000 | Appraisal (Lonestar Valuation Group), Executive summary
Appraisal NOI | 2656500 | Appraisal, Executive summary
Appraisal cap rate | 5.75% | Appraisal, Executive summary
Asking price above appraised value ($) | 1800000
Premium to appraised value | 3.896%
IN-PLACE NOI
Lease termination fee in T12 other income, Gulf Coast Vending, January 2026 | 142000 | GL Detail Other Income, account 4810
T12 roof repairs the OM adds back as non-recurring | 38000 | Offering Memorandum, Financial Analysis
Rent roll base rent not supported by executed leases | -114732 | Lease Abstract and Rent Roll Reconciliation, Reconciliation sheet
In-place NOI per OM | 2879326
(-) Rent roll variances: C-300, C-100 and F-300 | -114732
(-) One-time lease termination fee | -142000
Diligence-adjusted in-place NOI ($) | 2622594
OM in-place NOI overstatement | 256732
Overstatement as % of OM in-place NOI | 8.916%
Adjusted NOI cap rate on asking price | 5.464%
Value of adjusted NOI at the OM cap rate | 43709900
Value effect against asking price | -4290100
Further NOI at risk while the Building C roof leaks (roof repair add-back) | -38000
PHYSICAL CONDITION CAPITAL
Building C roof replacement (original 2001 BUR, active leaks), Years 1-2 | 612000 | Property Condition Assessment, Table 1
Parking and truck court mill and overlay, Buildings D-F, Year 3 | 185000 | Property Condition Assessment, Table 1
RTU replacements, 9 units past useful life, Years 1-5 | 126000 | Property Condition Assessment, Table 1
PCA immediate and short-term costs ($) | 923000
PCA total as reported | 923000 | Property Condition Assessment, Table 1
Check: computed less reported | 0
OM roof capital, Year 1 | 150000 | Offering Memorandum, Cash Flow Assumptions
PCA costs above OM roof capital | 773000
Building C roof above OM roof capital | 462000
ENVIRONMENTAL
Phase II subsurface investigation, low estimate | 18000 | Phase I ESA, Summary
Phase II subsurface investigation, high estimate | 25000 | Phase I ESA, Summary
REAL ESTATE TAXES
2026 appraised value, Denton CAD | 28400000 | Denton CAD 2026 Notice of Appraised Value
Combined tax rate | 2.25% | Denton CAD 2026 Notice of Appraised Value
Estimated 2026 taxes, computed | 639000
Estimated 2026 taxes per notice | 639000 | Denton CAD 2026 Notice of Appraised Value
Check: computed less notice | 0
Taxes if reassessed to the asking price | 1080000
Annual tax increase if reassessed to the asking price ($) | 441000
Taxes if reassessed to the appraised value | 1039500
Annual tax increase if reassessed to the appraised value | 400500
Vacant share of building area | 8.011%
Landlord share of the increase at current vacancy | 35329.7101
Days of 2026 before closing (seller's ownership) | 348
Days in 2026 | 365
Estimated 2026 tax proration credit to buyer | 609238.3562
FLOOD AND TITLE
Zone AE share of site area | 3.061%
Trailer stalls inside the item 9 easement, share of total | 58.33%
LEASES AND ESTOPPELS
C-300 remeasured to 9,200 SF | -8610 | Lease Abstract and Rent Roll Reconciliation, Reconciliation sheet
C-100 rent step of 11/1/2026 shown early | -5472 | Lease Abstract and Rent Roll Reconciliation, Reconciliation sheet
Rent roll error, C-300 and C-100 | -14082
F-300 rent on the rent roll with no executed lease | -100650 | Lease Abstract and Rent Roll Reconciliation, Reconciliation sheet
Total rent roll variance ($) | -114732
Check: total less reconciliation total | 0
B-200 free rent remaining after closing (credit to buyer) | 17283.87 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
C-200 unfunded TI allowance (tenant claims offset) | 38500 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
B-200 TI allowance per lease (Sec. 6.5), paid in full per estoppel v2 | 96000 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
A-100 base rent after the 6/30/2028 termination date | 1657032 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
A-100 termination fee, base rent component | 94926 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
B-100 fixed renewal against seller 2028 market rent, per year | -46710 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
Security deposits per leases | 226820.83 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
Security deposits confirmed by estoppels | 209227.5 | Lease Abstract and Rent Roll Reconciliation, Closing Items sheet
Deposits not confirmed by estoppel (C-400, F-300) | 17593.33
Earliest estoppel date returned (D-300) | 2026-09-08 | Estoppel Tracker
Latest estoppel date returned (F-400) | 2026-09-25 | Estoppel Tracker
Age of oldest estoppel at closing (days) | 98
Age of newest estoppel at closing (days) | 81
CLOSING CREDITS TO BUYER
B-200 free rent remaining after closing (diligence finding) | 17283.87
C-200 unfunded TI allowance (diligence finding) | 38500
Credits from diligence findings ($) | 55783.87
Tenant security deposits (routine closing item, not a diligence finding) | 226820.83
2026 real estate tax proration, estimate (routine closing item, not a diligence finding) | 609238.3562
Routine closing items ($) | 836059.1862
INDICATIVE VALUE AFTER DILIGENCE FINDINGS
Value of adjusted NOI at the OM cap rate | 43709900
(-) Building C roof replacement | -612000
Indicative value after diligence findings ($) | 43097900
Difference to asking price | -4902100
Difference to appraised value | -3102100
B-200 TI ALLOWANCE STATUS | Amount
B-200 TI allowance paid, per tenant estoppel version 2 (paid in full) | 96000 | B-200 tenant estoppel, version 2 (reported 22 Oct 2026)
Note on C10: Cedar Fork ALTA-NSPS Land Title Survey Report.pdf (page 2)
Note on C11: Cedar Fork Offering Memorandum.pdf (page 13)
Note on C12: Cedar Fork ALTA-NSPS Land Title Survey Report.pdf (page 2)
Note on C13: Cedar Fork ALTA-NSPS Land Title Survey Report.pdf (page 2)
Note on C14: Cedar Fork ALTA-NSPS Land Title Survey Report.pdf (page 2)
Note on C15: Cedar Fork ALTA-NSPS Land Title Survey Report.pdf (page 2)
Note on C18: Cedar Fork Appraisal 2026-09-01.pdf (page 3)
Note on C19: Cedar Fork Appraisal 2026-09-01.pdf (page 3)
Note on C20: Cedar Fork Appraisal 2026-09-01.pdf (page 3)
Note on C25: Cedar Fork GL Detail Other Income Oct-25 to Sep-26.xlsx (GL Detail A8:D8)
Note on C26: Cedar Fork Offering Memorandum.pdf (page 15)
Note on C27: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Reconciliation P25)
Note on C40: Cedar Fork Property Condition Assessment 2026-08-22.pdf (page 3)
Note on C41: Cedar Fork Property Condition Assessment 2026-08-22.pdf (page 3)
Note on C42: Cedar Fork Property Condition Assessment 2026-08-22.pdf (page 3)
Note on C44: Cedar Fork Property Condition Assessment 2026-08-22.pdf (page 3)
Note on C46: Cedar Fork Offering Memorandum.pdf (page 16)
Note on C51: Cited for C51:C52 Cedar Fork Phase I Environmental Site Assessment 2026-08-15.pdf (page 3)
Note on C55: Denton CAD 2026 Notice of Appraised Value.pdf (page 1)
Note on C56: Denton CAD 2026 Notice of Appraised Value.pdf (page 1)
Note on C58: Denton CAD 2026 Notice of Appraised Value.pdf (page 1)
Note on C6: Cedar Fork Offering Memorandum.pdf (page 5)
Note on C7: Cedar Fork Offering Memorandum.pdf (page 3)
Note on C75: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Reconciliation P13)
Note on C76: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Reconciliation P11)
Note on C78: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Reconciliation P23)
Note on C8: Cedar Fork Offering Memorandum.pdf (page 15)
Note on C81: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C12)
Note on C82: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C21)
Note on C83: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C25)
Note on C84: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C42)
Note on C85: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C40)
Note on C86: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C49)
Note on C87: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C53)
Note on C88: Cedar Fork Lease Abstract and Rent Roll Reconciliation.xlsx (Closing Items C54)
Note on C9: Cedar Fork Offering Memorandum.pdf (page 3)
Note on C90: Estoppel Tracker.xlsx (Estoppel Tracker B17:F17)
Note on C91: Estoppel Tracker.xlsx (Estoppel Tracker B23:F23)